## Project_Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 274 | 44 | 28 | 24 | 31 | 36 | 26 | 28 | 26 | 21 | 30 | 40 | 36 | 24 | 4
SPRINT 1 BACKLOG
US-01 | T01 | Research OWASP Top 10, secure coding guidelines, and code smell taxonomies | 2026-06-27 | 2026-06-28 | Developer | Research | Completed | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T02 | Study RAG architecture patterns: chunking, embeddings, and vector stores | 2026-06-28 | 2026-06-29 | Developer | Research | Completed | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T03 | Design multi-agent system architecture and define agent responsibilities | 2026-06-29 | 2026-07-01 | Developer | Design | Completed | 10 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T04 | Define orchestration flow and data models for findings and severity scoring | 2026-07-01 | 2026-07-02 | Developer | Design | Completed | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T05 | Build Code Submission Module: paste/upload UI with Python & Java syntax validation | 2026-07-02 | 2026-07-05 | Developer | Development | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T06 | Unit test the Code Submission Module | 2026-07-05 | 2026-07-06 | Developer | Testing | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-04 | T07 | Build Secure Coding Knowledge Base ingestion pipeline (chunking, embedding) | 2026-07-06 | 2026-07-09 | Developer | Development | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 4 | 0 | 0
US-04 | T08 | Configure vector store indexing and validate retrieval quality | 2026-07-08 | 2026-07-10 | Developer | Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0
SPRINT 2 BACKLOG
US-05 | T09 | Build Code Analysis Agent: code smell and complexity detection logic | 2026-07-11 | 2026-07-13 | Developer | Development | Completed | 12 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T10 | Implement severity scoring for Code Analysis Agent findings | 2026-07-13 | 2026-07-14 | Developer | Development | Completed | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T11 | Build Security Vulnerability Agent: OWASP vulnerability scanning logic | 2026-07-14 | 2026-07-17 | Developer | Development | Completed | 12 | 0 | 0 | 0 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T12 | Implement vulnerability classification and location-specific flagging | 2026-07-17 | 2026-07-19 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T13 | Implement multi-agent orchestration for parallel agent execution | 2026-07-19 | 2026-07-21 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0
US-07 | T14 | Merge agent outputs into a unified findings list | 2026-07-21 | 2026-07-22 | Developer | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
US-08 | T15 | Prepare sample Python/Java test codebases with known issues | 2026-07-21 | 2026-07-22 | Developer | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
US-08 | T16 | Validate agent detection accuracy and tune thresholds | 2026-07-22 | 2026-07-24 | Developer | Testing | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0
SPRINT 3 BACKLOG
US-09 | T17 | Build Remediation Agent: generate fix recommendations with corrected code examples for flagged findings | 2026-07-25 | 2026-07-27 | Developer | Development | Completed | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T18 | Implement best-practice explanation generation and link remediation guidance to severity findings | 2026-07-28 | Back | Developer | Development | Completed | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T19 | Build PR Summary Agent: compile agent outputs into a structured PR-style review summary | 2026-07-29 | 2026-07-30 | Developer | Development | Completed | 10 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T20 | Implement executive overview, severity breakdown, and prioritized fix list generation | 2026-07-31 | 2026-07-31 | Developer | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T21 | Develop Findings Display Module: severity-scored findings view with per-finding remediation | 2026-08-01 | 2026-08-02 | Developer | Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0
US-11 | T22 | Implement overall code health score calculation and developer portal dashboard UI | 2026-08-03 | 2026-08-03 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
US-13 | T23 | Build Conversational Code Assistant: RAG-powered chat interface for follow-up queries on flagged issues | 2026-08-04 | 2026-08-06 | Developer | Development | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 4 | 0
US-13 | T24 | Ground vulnerability explanations and secure coding guidance in indexed knowledge base retrieval | 2026-08-06 | 2026-08-07 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
SPRINT 4 BACKLOG
US-16 | T25 | Design report template and implement PDF export logic covering findings summary and severity breakdown | 2026-08-08 | 2026-08-11 | Developer | Development | Completed | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T26 | Implement remediation roadmap and code quality assessment sections; finalize report export | 2026-08-11 | 2026-08-12 | Developer | Development | Completed | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T27 | Conduct end-to-end testing across three sample Python/Java code samples of varying complexity | 2026-08-12 | 2026-08-14 | Developer | Testing | Completed | 10 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T28 | Validate detection accuracy, remediation quality, RAG retrieval relevance, and report completeness | 2026-08-14 | 2026-08-15 | Developer | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T29 | Optimize agent prompt design and standardize severity scoring consistency across agents | 2026-08-15 | 2026-08-17 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0
US-18 | T30 | Tune RAG retrieval quality and Conversational Code Assistant response accuracy | 2026-08-17 | 2026-08-18 | Developer | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
US-19 | T31 | Prepare technical documentation and final project report | 2026-08-18 | 2026-08-20 | Developer | Documentation | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0
US-19 | T32 | Prepare and rehearse final demonstration showcasing analysis across three distinct code samples | 2026-08-20 | 2026-08-21 | Developer | Documentation | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Sprint_Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 274 | 44 | 28 | 24 | 31 | 37 | 26 | 28 | 26 | 21 | 30 | 40 | 36 | 24 | 4
SPRINT 1 BACKLOG
US-01 | T01 | Research OWASP Top 10, secure coding guidelines, and code smell taxonomies | 2026-06-27 | 2026-06-28 | Developer | Research | Completed | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T02 | Study RAG architecture patterns: chunking, embeddings, and vector stores | 2026-06-28 | 2026-06-29 | Developer | Research | Completed | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T03 | Design multi-agent system architecture and define agent responsibilities | 2026-06-29 | 2026-07-01 | Developer | Design | Completed | 10 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T04 | Define orchestration flow and data models for findings and severity scoring | 2026-07-01 | 2026-07-02 | Developer | Design | Completed | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T05 | Build Code Submission Module: paste/upload UI with Python & Java syntax validation | 2026-07-02 | 2026-07-05 | Developer | Development | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T06 | Unit test the Code Submission Module | 2026-07-05 | 2026-07-06 | Developer | Testing | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
US-04 | T07 | Build Secure Coding Knowledge Base ingestion pipeline (chunking, embedding) | 2026-07-06 | 2026-07-09 | Developer | Development | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 4 | 0 | 0
US-04 | T08 | Configure vector store indexing and validate retrieval quality | 2026-07-08 | 2026-07-10 | Developer | Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0
SPRINT 2 BACKLOG
US-05 | T09 | Build Code Analysis Agent: code smell and complexity detection logic | 2026-07-11 | 2026-07-13 | Developer | Development | Completed | 12 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T10 | Implement severity scoring for Code Analysis Agent findings | 2026-07-13 | 2026-07-14 | Developer | Development | Completed | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T11 | Build Security Vulnerability Agent: OWASP vulnerability scanning logic | 2026-07-14 | 2026-07-17 | Developer | Development | Completed | 12 | 0 | 0 | 0 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T12 | Implement vulnerability classification and location-specific flagging | 2026-07-17 | 2026-07-19 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T13 | Implement multi-agent orchestration for parallel agent execution | 2026-07-19 | 2026-07-21 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0
US-07 | T14 | Merge agent outputs into a unified findings list | 2026-07-21 | 2026-07-22 | Developer | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
US-08 | T15 | Prepare sample Python/Java test codebases with known issues | 2026-07-21 | 2026-07-22 | Developer | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
US-08 | T16 | Validate agent detection accuracy and tune thresholds | 2026-07-22 | 2026-07-24 | Developer | Testing | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0
SPRINT 3 BACKLOG
US-09 | T17 | Build Remediation Agent: generate fix recommendations with corrected code examples for flagged findings | 2026-07-25 | 2026-07-27 | Developer | Development | Completed | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T18 | Implement best-practice explanation generation and link remediation guidance to severity findings | 2026-07-28 | 2026-07-28 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T19 | Build PR Summary Agent: compile agent outputs into a structured PR-style review summary | 2026-07-29 | 2026-07-30 | Developer | Development | Completed | 10 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T20 | Implement executive overview, severity breakdown, and prioritized fix list generation | 2026-07-31 | 2026-07-31 | Developer | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T21 | Develop Findings Display Module: severity-scored findings view with per-finding remediation | 2026-08-01 | 2026-08-02 | Developer | Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0
US-11 | T22 | Implement overall code health score calculation and developer portal dashboard UI | 2026-08-03 | 2026-08-03 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0
US-13 | T23 | Build Conversational Code Assistant: RAG-powered chat interface for follow-up queries on flagged issues | 2026-08-04 | 2026-08-06 | Developer | Development | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 4 | 0
US-13 | T24 | Ground vulnerability explanations and secure coding guidance in indexed knowledge base retrieval | 2026-08-06 | 2026-08-07 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
SPRINT 4 BACKLOG
US-16 | T25 | Design report template and implement PDF export logic covering findings summary and severity breakdown | 2026-08-08 | 2026-08-11 | Developer | Development | Completed | 12 | 12 | 8 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T26 | Implement remediation roadmap and code quality assessment sections; finalize report export | 2026-08-11 | 2026-08-12 | Developer | Development | Completed | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T27 | Conduct end-to-end testing across three sample Python/Java code samples of varying complexity | 2026-08-12 | 2026-08-14 | Developer | Testing | Completed | 10 | 0 | 0 | 0 | 0 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T28 | Validate detection accuracy, remediation quality, RAG retrieval relevance, and report completeness | 2026-08-14 | 2026-08-15 | Developer | Testing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T29 | Optimize agent prompt design and standardize severity scoring consistency across agents | 2026-08-15 | 2026-08-17 | Developer | Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | 0
US-18 | T30 | Tune RAG retrieval quality and Conversational Code Assistant response accuracy | 2026-08-17 | 2026-08-18 | Developer | Development | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
US-19 | T31 | Prepare technical documentation and final project report | 2026-08-18 | 2026-08-20 | Developer | Documentation | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | 0 | 0
US-19 | T32 | Prepare and rehearse final demonstration showcasing analysis across three distinct code samples | 2026-08-20 | 2026-08-21 | Developer | Documentation | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 2 | Secure-coding reference material was more fragmented than expected, slowing OWASP research | Consolidated sources into a single shared reading list and split topics across sessions
Sprint 1 | 5 | Agreeing on agent responsibility boundaries took longer than planned during architecture design | Ran a focused design review and documented agent contracts before continuing
Sprint 1 | 9 | Initial chunking strategy returned noisy retrieval results from the knowledge base | Tuned chunk size/overlap and re-indexed the vector store
Sprint 1 | 13 | File upload validation edge cases (mixed Python/Java files) needed extra handling | Added stricter file-type and syntax checks before hand-off to agents
Sprint 2 | 3 | Code Analysis Agent flagged too many false-positive code smells on first pass | Refined detection rules and severity thresholds against sample codebases
Sprint 2 | 7 | Security Vulnerability Agent needed clearer mapping from OWASP categories to severity levels | Defined a standard severity rubric and applied it consistently across finding types
Sprint 2 | 11 | Running both agents in parallel occasionally produced duplicate findings | Added a de-duplication/merge step before compiling the unified findings list
Sprint 2 | 14 | Validation against sample codebases surfaced a few missed vulnerability patterns | Extended test cases and re-validated detection accuracy before milestone close
Sprint 3 | 2 | Generating corrected code examples that matched each language's idioms took longer than expected | Built per-language remediation templates and validated fixes against sample findings
Sprint 3 | 5 | PR Summary Agent's severity breakdown didn't always align with underlying finding counts | Standardized the severity aggregation logic shared across agents
Sprint 3 | 9 | Findings Display dashboard felt cluttered once real finding volumes were loaded | Simplified the layout and grouped findings by severity tier
Sprint 3 | 13 | RAG retrieval for the Conversational Assistant occasionally returned answers outside the indexed knowledge base | Tightened retrieval grounding and added a fallback to cite 'not found in knowledge base'
Sprint 4 | 2 | Generating the PDF report layout consistently across varying finding volumes took longer than expected | Built a modular report template with dynamic sections that scale with finding counts
Sprint 4 | 5 | End-to-end tests on larger Java samples surfaced a few edge cases the agents had not seen | Added the edge cases to the sample test set and re-validated detection accuracy
Sprint 4 | 9 | Prompt tuning for the Conversational Code Assistant occasionally reduced retrieval precision | Iterated on prompt and retrieval settings together and re-tested against the knowledge base
Sprint 4 | 12 | Coordinating documentation, report generation, and demo prep in the same week created scheduling pressure | Sequenced remaining tasks and time-boxed documentation to keep the final demo on track

## Retrospection
SL | Sprint | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-06-27 | 2026-07-10 | Developer | Time-boxing research before moving to design | Deep-diving every OWASP sub-topic before starting design work | Documenting agent contracts and data models before coding | Adopted a shared reading list and stricter research time-box
2 | Sprint 2 | 2026-07-11 | 2026-07-24 | Developer | Validating agent output against sample codebases earlier in the sprint | Waiting until the end of the sprint to test detection accuracy | Running the two agents in parallel and merging results into one findings list | Added a de-duplication step and moved validation earlier in future sprints
3 | Sprint 3 | 2026-07-25 | 2026-08-07 | Developer | Demoing each agent's output as soon as it was built | Deferring UI polish on the dashboard until after all agents were wired up | Standardizing severity logic and grounding all AI outputs in the knowledge base | Adopted per-language remediation templates and a shared severity aggregation module
4 | Sprint 4 | 2026-08-08 | 2026-08-21 | Developer | Rehearsing the final demo incrementally as each module was finished | Leaving documentation until every other task was complete | Modular report design and grounding all agent outputs in the knowledge base | Time-boxed documentation and ran the final demo rehearsal a day ahead of delivery
5
6
7