## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team Member A | 2026-07-01 | File upload accepts .txt files instead of restricting to .py/.java extensions | Milestone 1 | Team Member A | Logical | Added file extension and MIME-type validation on upload handler | 2026-07-02 | Closed | Verified with sample .txt, .py, .java uploads
2 | Team Member B | 2026-07-03 | Pasted code containing tab characters breaks syntax validation and throws unhandled exception | Milestone 1 | Team Member B | Logical | Added input sanitization to normalize tabs/whitespace before validation | 2026-07-04 | Closed
3 | Team Member A | 2026-07-05 | Large OWASP guideline PDFs fail during chunking step, pipeline stops without an error message | Milestone 1 | Team Member A | Logical | Added try-catch with logging and reduced chunk size for large documents | 2026-07-06 | Closed | Root cause: chunk size exceeded embedding model token limit
4 | Team Member C | 2026-07-06 | Duplicate documents get re-indexed into vector store when the same file is uploaded twice | Milestone 1 | Team Member C | Logical | Implemented hash-based duplicate check before indexing | 2026-07-07 | Closed
5 | Team Member B | 2026-07-07 | Upload page does not show a progress indicator or confirmation after file upload completes | Milestone 1 | Team Member D | User Interface | Added upload progress bar and success toast notification | 2026-07-08 | Closed
6 | Team Member D | 2026-07-08 | Knowledge base indexing script has hardcoded file paths instead of using config values | Milestone 1 | Team Member D | Maintainability | Moved paths to a central config file | 2026-07-09 | Closed
7 | Team Member A | 2026-07-15 | Code Analysis Agent assigns 'High' severity to all long functions regardless of actual cyclomatic complexity | Milestone 2 | Team Member A | Logical | Fixed severity scoring logic to weight complexity metrics correctly | 2026-07-16 | Closed
8 | Team Member C | 2026-07-16 | Security Vulnerability Agent flags test/mock API keys in unit test files as hardcoded secrets (false positive) | Milestone 2 | Team Member C | Logical | Excluded test directories and added pattern allow-list for mock credentials | 2026-07-17 | Closed
9 | Team Member B | 2026-07-17 | Code Analysis Agent and Security Vulnerability Agent run sequentially instead of in parallel, increasing response time | Milestone 2 | Team Member B | Maintainability | Refactored orchestration to use async/parallel agent execution | 2026-07-18 | Closed | Reduced average response time noticeably in testing
10 | Team Member D | 2026-07-18 | Merged findings list shows duplicate entries when both agents flag the same line of code | Milestone 2 | Team Member D | Logical | Added de-duplication logic based on file, line number, and issue type | 2026-07-19 | Closed
11 | Team Member A | 2026-07-20 | Severity color coding is inconsistent — Medium severity findings sometimes display in red instead of orange | Milestone 2 | Team Member D | User Interface | Standardized severity color mapping in shared UI component | 2026-07-21 | Closed
12 | Team Member C | 2026-07-21 | Agent output JSON schema is inconsistent between Code Analysis Agent and Security Vulnerability Agent, causing frontend parsing errors | Milestone 2 | Team Member C | Standards | Defined and enforced a common findings schema across both agents | 2026-07-22 | Closed
13 | Team Member B | 2026-07-22 | Large Java files (1000+ lines) cause the Code Analysis Agent to time out | Milestone 2 | Team Member B | Others | Increased timeout threshold and added chunked analysis for large files | 2026-07-23 | closed | Needs further load testing before Milestone 3

## Sheet2
Logical
User Interface
Maintainability
Standards
Others